## Slide 1: Implementing a Trust-based digital phone system in Medicines Information
Amisha Gopal
Principal MI Pharmacist
London MI Service

## Slide 2: Why?
We are the first port of call
Digital phone system makes call handling smoother, including to staff based off-site or working from home
An audit showed we spend a significant amount of time re-directing phone calls to other departments including the dispensary
Benefits of the system
Improve experience of patients and staff
Other MI centres use similar digital systems

## Slide 3: Plan and progress
Review the audit results
Identify which system is available- chosen Cisco Jabber/Finesse
Regular communication with the team
Organise training and user testing
Make sure everyone is equipped
Embed training of the phone system into the new-starter’s checklist and relevant training paperwork at induction
Go-live! Launch date: 22/6/22
Monitor implementation for 6 months

## Slide 4: Summary of data collection
 | 2020 results (average for one month) | Month 1 Jul 22 | Month 2 Aug 22 | Month 3 Sep 22
Total time spent (mins) | 431 | 166 | 134 | 123
Total number of non- medicines calls | 73 | 46 | 41 | 31
Chart: Breakdown of non-medicines calls
| Colleague/ward/ clinic | Dispensary related | Pt transfer/discharge | Referal to GP/CP/A&E
Month 1 | 19 | 16 | 8 | 3
Month 2 | 15 | 11 | 12 | 3
Month 3 | 7 | 9 | 15 | 0
2020 average | 22 | 40 | 8 | 3

## Slide 5: Barriers to change
  Delay in response from external teams
  Reduction in non-essential team meetings due to COVID made communication difficult
  Change is hard to process. Added a regular agenda item in the team meetings to remind the team about this project and a chance to share any concerns/opinions
  Access to technology is a barrier to providing an efficient, seamless service

## Slide 6: Lessons learnt
Pay attention to the small details
Get to know the system
Be patient
Communication is key!
Map your stakeholders early on to ensure all key stakeholders receive communications
Support the Specialist Pharmacy Service plan on a national digital phone project